## Product
Total Project Tracking
Information in the columns A-G are filled in the project initiation (Iter1); columns G-J to be filled/updated by the end of each development iteration (Iter2-5)
# | Screen/Function | Data Entity/Table | Feature | Actor | Priority | Screen/Function Description | In Charge | Status | Planned | Actual | Updated | Update Details
1 | User Login | user | Common | Admin, Manager | 1 | Fields: User Name, Password User can choose Google Login using the FPT @fpt.edu.vn account | CuongNM | Done | iter1 | iter1 | none
2 | User Register | user | Common | User | 1 | Fields: Full Name, Email, Password | SonDH | Done | iter1 | iter1 | none
3 | Setting List | setting | Admin | Admin | 1 | Filters: Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive | DatDX | Done | iter1 | iter1 | iter5 | Fix type display name instead of id, ask before change status, show sider,/header/footer
4 | Setting Details | setting | Admin | Admin | 1 | Fields: Type (L), Title, Value, Display Order, Status, Description | TuanNQ | Done | iter1 | iter1 | none
5 | Password Reset | user | Common | User | 1 | Email -> Reset Link (Expirable) -> New Password, Verifying Password | SonDH | To Do | iter2 | iter2 | none
6 | User Profile | user | Common | User | 1 | Fields: Roll Number (R), Full Name, Email (R), Mobile, User Name, Profile Link, Role (R), Status (R) | SonDH | To Do | iter2 | iter2 | none
7 | Password Change | user | Common | User | 1 | Fields: Current Password, New Password, Verifying Password | SonDH | To Do |  | iter2 | none
8 | User List | user | Admin | Admin | 1 | Filters: Role, Status Column: Id, Roll Number, Full Name, User Name, Email, Mobile, Role, Status Row Actions: View/Edit, Activate/Deactivate (activating for Unverified status) Global Actions: Filter, Search (by Roll Number, Full Name, User Name, Email, or Mobile)), Sort (columns), Paginate Roles: admin ~ full access Status: Active, Inactive, Unverified | DatDX | To Do | iter2 | iter2 | iter5 | Add missing Role number row, Role display name instead of id, ask before make changes, update filter on click instead of click search by
9 | User Details | user | Admin | Admin | 1 | Fields: Id, Roll Number, Full Name, User Name, Email, Mobile, Profile Link, Role, Status, Note | DatDX | To Do | iter2 | iter2 | iter5 | Update validate for input field of user detail, ask before save
10 | Subject List | subject | Admin | Admin, Manager | 1 | Filters: Manager, Status Column: Id, Code, Name, Manager, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code, Name), Sort (columns), Paginate Roles: admin ~ full access, manager ~ read only Status: Active, Inactive | TuanNQ | To Do | iter2 | iter2 | none
11 | Subject Details | subject | Admin | Admin, Manager | 1 | Fields: Code, Name, Manager (L), Status, Description | TuanNQ | To Do |  | iter2 | none
12 | Subject Setting List | subject_setting | Manager | Manager | 1 | Filters: Subject (1), Type, Status Column: Id, Type, Title, Value, Display Order, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Title, Value), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | CuongNM | To Do | iter2 | iter2 | none
13 | Subject Setting Details | subject_setting | Manager | Manager | 1 | Fields: Subject (L), Type (L), Title, Value, Display Order, Status, Description | CuongNM | To Do | iter2 | iter2 | none
14 | Iteration List | iteration | Manager | Manager | 1 | Filters: Subject (1), Status Column: Id, Name, Eval Weight, On-Going, Status, Description Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Name), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | TungDS | Done | iter2 | iter2 | iter5 | Update Iteration List to always use Subject Filter and add check before Activate/Deactivate Iteration
15 | Iteration Details | iteration | Manager | Manager | 1 | Fields: Subject (L), Name, Evaluation Weight (%), On-Going Iteration, Status, Description | TungDS | Done | iter2 | iter2 | iter5 | Update required fields to not receive empty value
16 | User Authorization | user | System | All user | 2 | Link Check, Sider Menu, Header & Footer | TungDS | To Do | iter3 | iter3 | iter5 | Add filter to more screen and add a custom error page.
17 | Criteria List | evaluation_criteria | Manager | Manager | 2 | Filters: Subject(1), Iteration(1), Status Columns: Id, Name, Weight, Team Eval, Max LOC, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Name), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | TungDS | To Do | iter3 | iter3 | none
18 | Criteria Details | evaluation_criteria | Manager | Manager | 2 | Subject (R), Iteration (R), Evaluation Weight (%), Team Evaluation, Max LOC, Status, Description | TungDS | To Do | iter3 | iter3 | none
19 | Class List | class | Manager | Manager | 2 | Filters: Subject, Trainer, Term, Status Columns: Id, Subject, Code, Term, Block5, Trainer, Status Row Actions: View/Edit, Activate/Deactivate Global Actions: Filter, Search (by Code), Sort (columns), Paginate Roles: manager ~ full access, trainer ~ read only Status: Active, Inactive | TuanNQ | To Do | iter3 | iter3 | none
20 | Class Details | class | Manager | Manager | 2 | Subject (L), Code, Term (), Block5 Class, Trainer (L), Status | TuanNQ | To Do | iter3 | iter3 | none
21 | Class Setting List | class_setting | Trainer | Trainer | 2 | This screen will display a list of class setting in the system, will have the functions of searching for class setting, edit class setting | DatDX | Done | iter3 | iter3 | iter5 | Update validate for input field of add class setting, display type name instead of type ID, modify filter and add search by tittle , change status method , ask before make changes or save
22 | Class Setting Details | class_setting | Trainer | Trainer | 2 | This screen will display the class setting's information, from this screen can update the information the class setting | DatDX | Done | iter3 | iter3 | iter5 | Fix name incorect(title - type), load from database not hard fix, add header/footer, validate length
23 | Milestone List | milestone | Trainer | Trainer | 2 | This screen will display a list of Milestone in the system, will have the functions of searching for milestone, edit milestone | DatDX | Done | iter3 | iter3 | iter5 | Update validate for input field of add milestone, modify filter and search function, change status method , ask before make changes or save
24 | Team List |  | Trainer | Trainer | 2 | display a list of on-going teams and projects | SonDH | To Do | iter3 | iter3 | none
25 | Team Details |  | Trainer | Trainer | 2 | show detail of a team | SonDH | To Do | iter3 | iter3 | none
26 | Student List |  | Trainer | Trainer | 2 | Filters: Team, Status Columns: Team, Full Name, Email, Roll Number, Team Leader, Status The list is sort automatically by the Team Code Row Actions: Change Team, Set As Team Leader, Activate/Deactivate Global Actions: Filter, Search (by Full Name, Email, Roll Number), Export Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | CuongNM | To Do | iter3 | iter3 | none
27 | Student import |  | Trainer | Trainer | 2 | Team, Full Name, Email, Roll Number, Team Leader, Status | CuongNM | To Do | iter3 | iter3 | none
28 | Milestone Details | milestone | Trainer | Trainer | 2 | Display the information of milestone, with the functions of updating milestone information | DatDX | Done | iter4 | iter4 | iter5 | fix filter by iteration, fix class list to correct form, separate add and detail
29 | Function List |  | Student | Student | 2 | the list of functions being performed by the student group | SonDH | To Do | iter4 | iter4 | none
30 | Function Detail |  | Student | Student | 2 | details of the function being performed | SonDH | To Do | iter4 | iter4 | none
31 | Function Import |  | Student | Student | 3 | Add function to the system to update the list | SonDH | To Do | iter4 | iter4 | none
32 | Tracking List |  | Tracking | Tracking | 3 | Show list tracking , search , add, remove update | CuongNM | To Do | iter4 | iter4 | none
33 | Tracking Detail |  | Tracking | Tracking | 3 | Ajdust functions for implementing in the milestone name | CuongNM | To Do | iter4 | iter4 | none
34 | New Tracking |  | Tracking | Tracking | 3 | Show tracking detail , History tracking , evalution loc and update | CuongNM | To Do | iter4 | iter4 | none
35 | Issue List |  | Student | Student | 3 | the list of issues being performed by the student group | TuanNQ | To Do | iter4 | iter4 | none
36 | Issue Sync |  | System | System | 3 | Synchronize issues in the SPM system and related GitLab project issues. Includes type, status and labels | TuanNQ | To Do | iter4 | iter4 | none
37 | Iteration Evaluations |  | Evaluation | Evaluation | 3 | Evaluate the work process of individuals through student numbers | TuanNQ | To Do | iter4 | iter4 | none
38 | Milestone Submit | team_evaluation, evaluation_criteria, team | Student | System | 3 | Synchronize issues in the SPM system and related GitLab project issues. Includes type, status and labels | DatDX | Done | iter4 | iter4 | iter5 | Add collapse for button, Logical error correction, update load submited case and load criteria name from database instead of hard fix, add cases committed, evaluated, submitted
39 | Student Evaluations | iteration_evaluation, member_evaluation, loc_evaluation | Evaluation | System | 3 | Synchronize issues in the SPM system and related GitLab project issues. Includes type, status and labels | DatDX | Done | iter4 | iter4 | iter5 | Update filter by student name, Add collapse for button, add label to display student information, Logical error correction, update load result from database instead of hard fix
40 | Tracking Updates | tracking, update | Student | Student | 3 | Allow student to update evaluated function. Add, edit, or view updating record. Display update history as well as evaluating comment. | TungDS | Done | iter4 | iter4 | none
41 | Tracking Submit | submit | Student | Student | 3 | Track and allow user to choose and update assignee and submit selected functions. | TungDS | Done | iter4 | iter4 | none

## Iter1
Iteration Tracking - Iteration 1
Information in the columns C-I must be provided as results of the iteration 1
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Home | Common | Default screen where all users can visit. There have information of system, contact of developer. The site can lead to login page and register page | TungDS | Done | II.1 | II.1
2 | User Register | Common | Screen where users can create new account with personal information. Click Submit to submit new account | SonDH | Done
3 | User Login | Common | Screen where the user logs into the system with the registered account. If the account or password is wrong, the system will notify the user | CuongNM | Done
4 | Dashboard | Common | The screen shows all the main functions of the system, the admin will have access to the most functions, different roles will display a different number of functions depending on the user's rights | TungDS | Done | II.2 | II.2
5 | Setting List | Admin | Show the paginated list of settings and its properties. Only admin can filter the setting by type, status Allow the admin to search settings by value. The list is sortable by id, type, value, order, status. From each setting, the admin can choose to view, activate/deactivate, or edit it. The page also has the button/link that allows the admin to add new setting | DatDX | Done | II.5.1 | II.5.1
6 | Setting Details | Admin | Show detailed user information, from that allow the user to edit setting information | TuanNQ | Done | II.5.2 | II.5.2

## Iter2
Iteration Tracking - Iteration 2
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
-2 | Password Reset | Common | Allow user to reset password using registered gmail in case user forgot password | SonDH | Doing
-1 | User Profile | Common | Display information about the user who is logged in to the system | SonDH | Done
0 | Password Change | Common | The user can access this screen from the dropdown on the header. At this screen the user will enter the old password, the new password and click "Change Password" to change the password | SonDH | Done
1 | User List | Admin | This screen will display a list of users in the system, will have the functions of searching for users, adding users | DatDX | Done | II.10.1 | II.10.1
2 | User Details | Admin | This screen will display the user's information, from this screen can update the information the user | DatDX | Done | II.10.2 | II.10.2
3 | Subject List | Admin | Display the list of subjects, each user role will see different subjects. This screen has the functions of searching, adding and editing subjects | TuanNQ | Done | II.6.1 | II.6.1
4 | Subject Details | Admin | Display the information of the subject, with the functions of updating subject information | TuanNQ | Done | II.6.2 | II.6.2
5 | Subject Setting List | Manager | Show the paginated list of settings (include settings' id, type, value, order, status): The admin can filter the setting by type, status Allow the admin to search settings by value The list is sortable by id, type, value, order, status From each setting, the admin can choose to view, activate/deactivate, or edit it The page also has the button/link that allows the admin to add new setting | CuongNM | To Do
6 | Subject Setting Details | Manager | Show detailed user information (type, value, order, description, status), from that allow the user to add new, view or edit setting information | CuongNM | To Do
7 | Iteration List | Manager | Displays the list of iterations of the subject, has searchand filter functions | TungDS | Done | II.7.1 | II.7.1
8 | Iteration Details | Manager | Display the contents of the iteration, perform operations to edit the content of the iteration | TungDS | Done | II.7.2 | II.7.2

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | User Authorization | system | Allow users to access different pages and different functions based on their role. | TungDS | Doing | II.12 | II.12
2 | Criteria List | Manager | Displays the list of criteria of the evaluation, has search and filter functions | TungDS | Done | II.13.1 | II.13.1
3 | Criteria Details | Manager | Display the contents of the criteria, perform operations to edit the content of the criteria | TungDS | Done | II.13.2 | II.13.2
4 | Class List | Manager | Displays the list of classes, has search and filter functions | TuanNQ | Done | II.14.1 | II.14.1
5 | Class Details | Manager | Display the information of class, with the functions of updating class information | TuanNQ | Done | II.14.2 | II.14.2
6 | Class Setting List | Trainer | This screen will display a list of class setting in the system, will have the functions of searching for class setting, edit class setting | DatDX | Done | II.15.1 | II.15.1
7 | Class Setting Details | Trainer | This screen will display the class setting's information, from this screen can update the information the class setting | DatDX | Done | II.15.2 | II.15.2
8 | Milestone List | Trainer | This screen will display a list of Milestone in the system, will have the functions of searching for milestone, edit milestone | DatDX | Done | II.16.1 | II.16.1
9 | Team List | Trainer | display a list of on-going teams and projects | SonDH | Doing | II.22 | II.20
10 | Team Details | Trainer | show detail of a team | SonDH | Doing | II.23 | II.21
11 | Student List | Trainer | Filters: Team, Status Columns: Team, Full Name, Email, Roll Number, Team Leader, Status The list is sort automatically by the Team Code Row Actions: Change Team, Set As Team Leader, Activate/Deactivate Global Actions: Filter, Search (by Full Name, Email, Roll Number), Export Roles: trainer ~ full access, student ~ read only Status: Active, Inactive | CuongNM | To Do
12 | Student import | Trainer | Team, Full Name, Email, Roll Number, Team Leader, Status | CuongNM | To Do

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Function List | Student | the list of functions being performed by the student group | SonDH | To Do
2 | Function Detail | Student | details of the function being performed | SonDH | To Do
3 | Function Import | Student | Add function to the system to update the list | SonDH | To Do
4 | Tracking List | Tracking | Show list tracking , search , add, remove update | CuongNM | To Do
5 | Tracking Detail | Tracking | Ajdust functions for implementing in the milestone name | CuongNM | To Do
6 | New Tracking | Tracking | Show tracking detail , History tracking , evalution loc and update | CuongNM | To Do
7 | Issue List | Student | the list of issues being performed by the student group | TuanNQ | Done | II.18.1 | II.22.1
8 | Issue Sync | System | Synchronize issues in the SPM system and related GitLab project issues. Includes type, status and labels | TuanNQ | To Do | II.18.2 | II.22.2
9 | Iteration Evaluations | Evaluation | Evaluate the work process of individuals through student numbers | TuanNQ | Done | II.19 | II.23
10 | Milestone Details | Trainer | Display the information of milestone, with the functions of updating milestone information | DatDX | Done | II.16.2 | II.16.2
11 | Milestone Submit | Student | Allow user to choose and submit selected function | DatDX | Done | II.16.3 | II.16.3
12 | Student Evaluations | Evaluation | Evaluate the work process of student through student numbers | DatDX | Done | II.17 | II.17
13 | Tracking Updates | Student | Allow student to update evaluated function. Add, edit, or view updating record. Display update history as well as evaluating comment. | TungDS | Done | II.20 | II.18
14 | Tracking Submit | Student | Track and allow user to choose and update assignee and submit selected functions. | TungDS | Doing | II.21 | II.19 | Currently can only view submit list. Not being able to submit or update submission yet

## Iter5
Iteration Tracking - Iteration 5
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
1 | Update User Authorization | System | Update authorization filter for the rest of the system based on user's role. | TungDS | Done | II.12 | II.12
2 | Update Iteration List | Manager | Update Iteration List functionality based on feedback. | TungDS | Done | II.7.1 | II.7.1
3 | Update Iteration Details | Manager | Update Iteration List functionality based on feedback. | TungDS | Done | II.7.2 | II.7.2
4 | Web Contacts | Common | Allow user as well as guest to use the form in web footer to submit a contact. | TungDS | Done | II.25 | II.24
5 | Update Setting List | Admin | Fix type display name instead of id, ask before change status, show sider,/header/footer | DatDX | Done | II.5.1 | II.5.1
6 | Update User List | Admin | Add missing Role number row, Role display name instead of id, ask before make changes, update filter on click instead of click search by | DatDX | Done | II.10.1 | II.10.1
7 | Update User Detail | Admin | Update validate for input field of user detail, ask before save | DatDX | Done | II.10.2 | II.10.2
8 | Update Class Setting List | Trainer | Update validate for input field of add class setting, modify filter and search function, change status method , ask before make changes or save | DatDX | Done | II.15.1 | II.15.1
9 | Update Class Setting Detail | Trainer | Update validate for input field of class setting detail | DatDX | Done | II.15.2 | II.15.2
7 | Update Milestone List | Trainer | Update validate for input field of add milestone, modify filter and search function, change status method , ask before make changes or save | DatDX | Done | II.16.1 | II.16.1
8 | Update Milestone Detail | Trainer | Update validate for input field of milestone detail | DatDX | Done | II.16.2 | II.16.2
9 | Update Milestone Submit | Student | Add collapse for button, Logical error correction, update load submited case and load criteria name from database instead of hard fix, add cases committed, evaluated, submitted | DatDX | Done | II.16.3 | II.16.3
10 | Update Student Evaluation | Evaluation | Update filter by student name, Add collapse for button, add label to display student information, Logical error correction, update load result from database instead of hard fix | DatDX | Done | II.17 | II.17
11 | Update Subject List | Admin | Update form of subject, add more filter, sort, fix paginate | TuanNQ | Done | II.6.1 | II.6.1
12 | Update Subject Details | Admin | update class information update section to database | TuanNQ | Done | II.6.2 | II.6.2
13 | Update Class List | Manager | Update form of classes list, add more filter, fix paginate | TuanNQ | Done | II.14.1 | II.14.1